## Task Analysis
Pronith Laboratory Task Analysis
Pay Per Hour |  | 2.5
Working Hour Per Day |  | 2
Developer Resource |  | 3
ID | Group | Task | Duration | Notes | Day | Who | Total Day
1 | System Analysis | Project Document & Preparation Setup | 6 |  | 1.5 | Vannak | 5.5
2 |  | Database Design | 8 |  | 2
3 |  | Template Project Design | 8 |  | 2
4 | User Manager | Login Manager | 2 |  | 0.5 | Sochy | 2.5
5 |  | Manage User -Add/Edit/Delete user -User has two type super-admin & admin | 4 |  | 1
6 |  | Manage Profile -User manage his profile & change password | 4 |  | 1
7 | Patient Manager | Manage Partient -Partient, should has doctor reference if has | 2 |  | 0.5 | Vannak | 0.5
8 | Doctor Manager | Manage Doctor | 4 |  | 1 | Vannak | 1
9 | Ill Manager | Manage Group of ill | 2 |  | 0.5 | Sochy | 4
10 |  | Manage ill | 3 |  | 0.75
11 |  | Manage sub-item test of ill divided by male and female | 3 |  | 0.75
12 |  | Mape sub-item test of ill with ill, and group of ill | 8 |  | 2
13 | Ill Test Manager | Manage the Blood Test Manager -can filter to view the blood test list by date, partient, doctor, result issue, receive issue -be able to select for edit or delete | 16 | It's in homepage of blood test manager | 4 | Vannak | 11.25
14 |  | Register blood test -issue the blood item test -issue the payment -issue the invoice of payment -print out for customer | 12 | This process doesn't complete only one time. -First come is just register the blood test item. -Second, issue the invoice with item list selected -Third, input the result after got result after doctor and print the final result out -Fourth, publis that is the test result has been recieved or not yet. | 3
15 |  | Edit Blood Test -issue to update incase has wrong information and the action is the same as Register blood test | 3 |  | 0.75
16 |  | Result Blood Test -select which blood test item and input the result -issue the result and print out | 8 |  | 2
17 |  | Receive Result & Payment -after gave printed result to partient, they need to pay in case case they are not yet completed payment and print invoice | 4 |  | 1
18 |  | Delete Bloodtest -also delete other info related such as invoice history | 2 |  | 0.5
| Doctor Commission | Doctor commission manager -view the commission of each doctor -filter to see the doctor income and can filter by issue income, date | 4 |  | 1 | Sophea | 2
|  | Doctor Commission Payment -issue the payment for the doctor of his commission income -issue the invoice when he come to get his commission | 4 |  | 1
19 | Report Manager -Note: all report has print out option | Blood Test Report -Filter by patient, by doctor, date, issue result, issue receive, ill | 12 |  | 3 | Sochy | 8.25
20 |  | Partient Report -Filter by date, doctor, ill | 6 |  | 1.5
21 |  | Doctor Report -Filter by date | 3 |  | 0.75
23 |  | Finance Report -Filter by date, daily, monthly, fromt-to | 12 |  | 3
24 | Testing | Test All Task | 10 |  | 2.5 | Sophea | 2.5
25 | Risk | For unexpected risk | 10 |  | 2.5 | Sophea | 2.5
Total Hour |  |  | 160
Total Price |  |  | 400
Total Estimated Day |  |  | 80
Total Estimated Day By Resource |  |  | 26.6667
| Developer | Number of Day | Number of Hour
| Sopea | 7 | 28
| Vannak | 18.25 | 73
| Sochy | 14.75 | 59

## Quotation
Pronith Laboratory System |  |  | Tel: 017 37 57 60
Pronith Laboratory Quotation List
For Customer
Company name |  | Pronith Laboratory
Address
Contact Person
Tel
Email
For Company
Company Name |  | Group Free Lancer Development
Address |  | #21B, st. 271, Teuk Laok 3, Tual Kok, Phnom Pneh, Cambodia
Contact Person |  | OU Sophea
Tel |  | 017 37 57 60
Dear sir/mardam, Please find the quotation of our proposal to developer of Pronith Laboratory System below
No | Task | Description | Price
1 | System Analysis | -Database design -Template design -Documentation -Testing | 40
2 | User Manager | +Login Manager +Manage User -Add/Edit/Delete user -User has two type super-admin & admin +Manage Profile -User manage his profile & change password | 40
3 | Patient Manager | +Manage Partient -Partient, should has doctor reference if has | 20
4 | Doctor Manager | +Manage Doctor -one doctor can has reference by another doctor | 20
5 | Ill Test Manager | +Manage Group of ill +Manage ill +Manage sub-item test of ill divided by male and female +Mape sub-item test of ill with ill, and group of ill | 60
6 | Blood Test Manager | +Manage the Blood Test Manager -Can filter to view the Blood Test list by date, partient, doctor, result issue, receive issue -Be able to select for edit or delete +Register Blood Test -Issue the doctor commission in case partient come by reference of doctor, other doctor that referenced with that doctor would get commission as well -Issue the Blood item Test -Issue the payment -Issue the invoice of payment -Print out for customer +Edit Blood Test -Issue to update incase has wrong information and the action is the same as Register Blood Test +Result Blood Test -Select which Blood Test item and input the result -Issue the result and print out +Receive result & payment -After gave printed result to partient, they need to pay in case case they are not yet completed payment and print invoice +Delete Bloodtest -Also delete other info related such as invoice history | 120
7 | Report Manager | +Blood Test Report -Filter by patient, by doctor, date, issue result, issue receive, ill +Partient Report -Filter by date, doctor, ill +Doctor Report -Report about the commission income -Filter by date, issue paid +Ill Test Report -Filter by date created, group of ill +Finance Report -Filter by date, daily, monthly, from date - to date | 60
8 | Doctor Commission | +Manage on doctor commission -Generate the doctor commission from partient register. +Administrator can add percentage as manual +Issue the payment to the doctor +Issue invoice to doctor when pay | 40
|  | Total | 400
Term and Condition
Payment will be issued in 3 steps -First step at the beginning of project start (30% if titak ammount) -Second step after project has completed 50% (30% of total ammount) -Third step after the project has been completed 100% (40% of total ammount)
After agreed between developer and customer, money paid couldn't be refund back
In case developer couldn't complete in any requirement, we will return back on that module
We will free support for 6months after product released
We hope our offer will meet to your requirements, and we are looking forward to receiving your order confirmation soon. Your Sincerely,
Developer Signature |  | Customer Signature

## Task All
No | Task Name |  | Hour | Duration | Start | End | Complete | Delay
1 | System Analysis | PEN Vannak | 22 | 5.5 | 2013-08-15 20:00 | 2013-08-20 06:00 | 100 | 0
2 | User Manager | CHOEURN Sochy | 10 | 2.5 | 2013-08-25 20:00 | 2013-08-28 01:00 | 100 | 0
3 | Doctor Manager | PEN Vannak | 4 | 1 | 2013-08-27 20:00 | 2013-08-28 | 0 | 0
4 | Patient Manager | PEN Vannak | 2 | 0.5 | 2013-08-28 20:00 | 2013-08-28 22:00 | 0 | 0
5 | Ill Manager | CHOEURN Sochy | 16 | 4 | 2013-08-29 20:00 | 2013-08-31 08:00 | 0 | 0
6 | Ill Test Manager | PEN Vannak | 45 | 11.25 | 2013-09-01 20:00 | 2013-09-06 21:00 | 0 | 0
7 | Doctor Commission | OU Sophea | 8 | 2 | 2013-09-05 20:00 | 2013-09-06 23:00 | 0 | 0
8 | Report Manager | CHOEURN Sochy | 33 | 8.25 | 2013-09-03 20:00 | 2013-09-10 | 0 | 0
9 | Test All Task | OU Sophea | 10 | 2.5 | 2013-09-06 20:00 | 2013-09-10 01:00 | 0 | 0
10 | For unexpected risk | OU Sophea | 10 | 2.5 | 2013-09-10 20:00 | 2013-09-12 01:00 | 0 | 0
|  | PEN Vannak | 73 | 18.25
|  | OU Sophea | 28 | 7
|  | CHOEURN Sochy | 59 | 14.75